## Sheet1
Work Item Type | Title | Description | Priority | Status
Epic 1 | Mobile Application Development | Develop a mobile application for field researchers to collect real-time wildlife data and interact with IoT devices. | High | In progress
User story 1 | Capture wildlife observations | As a field researcher, I want to be able to record wildlife sightings, behaviors, and health conditions through the mobile app, so that I can contribute data in real time. | High | In progress
Task 1 | Design User Interface for Observation | Design a simple, intuitive interface for entering wildlife observations on mobile devices. | High | In progress
Task 2 | Implement Observation Entry Logic | Code the logic for capturing animal sightings, behaviors, and health conditions, ensuring data validation and synchronization. | High | To Do
Subtask 1 | Enable Text and Voice Notes | Implement functionality for researchers to input data via text or voice notes to enhance data accuracy and speed. | Medium | To do
Epic 2 | Web Application Development | Develop a web-based administrative interface to manage wildlife data, analyze patterns, and manage system settings. | High | To Do
User story 2 | Admin Data Analysis | As an administrator, I want to be able to view and analyze collected wildlife data, so I can make informed decisions for wildlife management. | High | To do
Task 3 | Design Data Analysis Dashboard | Create wireframes for the dashboard that will display wildlife data and analytics for administrators. | Medium | In progress
Task 4 | Implement Data Aggregation Logic | Develop backend logic for aggregating wildlife data (e.g., sightings, behavior, location) from mobile and IoT sources into a comprehensive view for the admin | High | To do
Epic 3 | IoT Device Integration And Management | Implement integration of IoT devices (e.g., GPS collars, motion sensors) and ensure data is properly captured and transmitted to the system. | High | Almost completed
User story 3 | Integrate GPS-enabled Animal Collars | As a system developer, I want to integrate GPS-enabled animal collars into the WATMS system so that real-time animal movements are tracked. | Medium | In progress
User story 4 | Integrate Motion Sensors | As a system developer, I want to integrate motion sensors into the WATMS system to monitor wildlife activity and detect significant behavior changes. | Low | To do
Epic 4 | Multi-language Support | Implement multi-language support in mobile and web applications, including English, French, Spanish, and Swahili. | Medium | To do
User story 5 | Language Switch for Mobile App | As a field researcher, I want to switch between different languages (English, French, Spanish, Swahili) in the mobile app so that I can work in my preferred language. | Very high | Almost completed
Task 5 | Translate Web UI Text to French | Translate the web app's UI text to French and ensure proper integration for display when French is selected as the language. | High | In progress
Task 6 | Implement Language Switcher UI | Implement a language toggle for the web app to allow administrators to switch between English and French. | High | To do
User story 6 | Language Switch for Web App | As an administrator, I want to switch between English and French in the web app so that I can use the application in my preferred language. | High | To Do
Epic 5 | End-to-End Encryption for Data | As a system architect, I want to implement end-to-end encryption for all communication between IoT devices, mobile/web apps, and the server to ensure data security. | Critical | In progress